## Backlog
SER594 Dungeon MVP Development Backlog
Total Tasks | 40 | Not Started | 40 | In Progress | 0 | Done | 0 | Blocked | 0 | 0%
Planning basis: MVP Game Design and Requirements Specification v1.0. Owners and schedules are team inputs.
ID | Milestone | Epic | Task | Priority | Complexity | Depends On | Suggested Role | Owner | Status | Acceptance Criteria
SET-01 | M0 Foundation | Project Setup | Confirm the team input policy and keep Both input backends enabled during migration. | P0 | S |  | Tech Lead |  | Not Started | The policy is documented and all team members use the same project setting.
SET-02 | M0 Foundation | Project Setup | Create the Assets/_Game folder structure without moving existing prototype assets. | P0 | S | SET-01 | Tech Lead |  | Not Started | The agreed folders exist and the current SampleScene still opens without missing references.
SET-03 | M0 Foundation | Scenes | Create Bootstrap, MainMenu, RouteMap, Combat, and RunComplete scenes. | P0 | M | SET-02 | Unity Generalist |  | Not Started | All planned scenes open and appear in Build Settings in the approved order.
SET-04 | M0 Foundation | Core State | Implement GameSession and the mutable RunState and PlayerRunState models. | P0 | M | SET-02 | Systems |  | Not Started | One authoritative run state survives scene changes and initializes with the approved values.
SET-05 | M0 Foundation | Scene Flow | Implement valid scene transitions through a SceneFlowService. | P0 | M | SET-03, SET-04 | Systems |  | Not Started | The application can move from Bootstrap to MainMenu and start a clean run without duplicate services.
DATA-01 | M0 Foundation | Data | Define player, enemy, boss, potion, and weapon data structures. | P0 | M | SET-04 | Systems |  | Not Started | All approved MVP values are represented once and can be read by runtime systems.
DATA-02 | M0 Foundation | Data | Create static definitions or configuration assets for enemies, items, events, and combat. | P1 | M | DATA-01 | Systems |  | Not Started | Design values can be edited without changing unrelated runtime logic.
FLOW-01 | M1 Game Flow | Stage Flow | Implement StageGenerator for Stage 1-1, Stages 1-2 to 1-4, and Stage 1-5. | P0 | M | SET-04 | Systems |  | Not Started | Generated choices follow fixed-stage, exclusion, distinct-choice, and combat-repeat rules.
FLOW-02 | M1 Game Flow | Route UI | Build the route-selection screen and connect node buttons to the active run. | P0 | M | FLOW-01, SET-05 | UI |  | Not Started | The screen displays the correct number and type of choices and records one legal selection.
FLOW-03 | M1 Game Flow | Run Lifecycle | Implement new-run initialization, run abandonment, and return-to-menu reset. | P0 | M | SET-04, SET-05 | Systems |  | Not Started | Starting or abandoning a run produces a clean state with no values from the prior run.
HEX-01 | M2 Hex Grid | Hex Math | Implement axial hex coordinates, equality, neighbors, and distance. | P0 | M | SET-02 | Combat Systems |  | Not Started | Hex coordinate operations return correct deterministic results in EditMode tests.
HEX-02 | M2 Hex Grid | Board Generation | Generate the pointy-topped radius-3 combat board. | P0 | M | HEX-01 | Combat Systems |  | Not Started | The generated board contains exactly 37 unique hexes.
HEX-03 | M2 Hex Grid | Board Presentation | Convert axial coordinates to world positions and render selectable hex visuals. | P0 | M | HEX-02 | Combat Systems |  | Not Started | Every logical hex has one correctly positioned visual and click target.
HEX-04 | M2 Hex Grid | Movement | Calculate reachable cells and display legal movement highlights. | P0 | L | HEX-01, HEX-03 | Combat Systems |  | Not Started | A unit with movement 3 sees only legal unoccupied destinations within range.
HEX-05 | M2 Hex Grid | Pathfinding | Implement occupancy checks and shortest-path movement for the enemy. | P0 | L | HEX-04 | Combat Systems |  | Not Started | The enemy reaches the closest legal hex without entering occupied or invalid cells.
COM-01 | M3 Combat | Combat Flow | Implement CombatController and explicit combat phases. | P0 | L | SET-04, HEX-02 | Combat Systems |  | Not Started | Only valid phase transitions occur and one controller owns the active turn.
COM-02 | M3 Combat | Initiative | Implement D20 initiative with rerolls on ties. | P0 | S | COM-01 | Combat Systems |  | Not Started | The higher roll acts first and a tied result never selects a winner.
COM-03 | M3 Combat | Player Turn | Implement player movement, skip movement, and action selection. | P0 | L | COM-01, HEX-04 | Combat Systems |  | Not Started | The player receives one movement phase and one action, and invalid input consumes neither.
COM-04 | M3 Combat | Attack Rules | Implement attack rolls, Armor Class checks, damage dice, and HP changes. | P0 | M | COM-01, DATA-01 | Combat Systems |  | Not Started | Hit, miss, damage, and zero-HP results match the approved formulas.
COM-05 | M3 Combat | Potion Action | Implement potion use during combat and outside combat. | P1 | M | COM-03, SET-04 | Systems |  | Not Started | A potion heals up to 20 HP, never exceeds maximum HP, and consumes a combat action.
COM-06 | M3 Combat | Enemy Turn | Implement enemy range checks, movement, and attack behavior. | P0 | L | COM-01, COM-04, HEX-05 | Combat Systems |  | Not Started | The enemy attacks in range or moves toward the player and attacks when newly in range.
COM-07 | M3 Combat | Combat Results | Implement victory, defeat, normal rewards, and boss completion transitions. | P0 | M | COM-04, COM-06 | Systems |  | Not Started | Combat ends exactly once and opens the correct result, defeat, or completion state.
COM-08 | M3 Combat | Retry | Capture and restore the complete pre-combat retry snapshot. | P0 | M | SET-04, COM-07 | Systems |  | Not Started | Retry restores HP, maximum HP, EXP, gold, potions, weapon, and stage state.
COM-09 | M3 Combat | Combat UI | Build the combat HUD, turn indicator, highlights, action controls, and combat log. | P0 | L | COM-03, COM-04, COM-06 | UI |  | Not Started | The player can identify the active turn, legal actions, unit stats, and every roll result.
NODE-01 | M4 Meta Nodes | Shop | Implement potion and weapon purchases with price and purchase limits. | P0 | M | FLOW-02, DATA-01 | UI and Systems |  | Not Started | Purchases enforce gold costs, per-visit limits, and weapon replacement.
NODE-02 | M4 Meta Nodes | Reward | Implement the 50 percent potion or weapon reward node. | P0 | S | FLOW-02, DATA-01 | Systems |  | Not Started | The node grants exactly one valid reward and applies weapon replacement correctly.
NODE-03 | M4 Meta Nodes | Event | Implement Event 1 choices and Constitution check. | P0 | M | FLOW-02, DATA-02 | UI and Systems |  | Not Started | All three Event 1 choices apply the approved costs, check, rewards, and damage.
NODE-04 | M4 Meta Nodes | Event | Implement Event 2 choices and Strength check. | P0 | M | FLOW-02, DATA-02 | UI and Systems |  | Not Started | All three Event 2 choices apply the approved weapon, HP, maximum HP, and gold results.
PROG-01 | M4 Meta Nodes | Progression | Implement EXP gain and leveling without healing current HP. | P0 | S | SET-04, COM-07 | Systems |  | Not Started | Every 10 EXP increases maximum HP by 5 and preserves current HP.
PROG-02 | M4 Meta Nodes | Weapons | Implement accuracy and damage weapon effects with replacement behavior. | P0 | M | DATA-01, COM-04 | Systems |  | Not Started | Accuracy produces a total +4 attack bonus and damage changes from 1D10 to 2D10.
PROG-03 | M4 Meta Nodes | Rewards | Implement 5 gold, 5 EXP, and 25 percent potion combat rewards. | P0 | S | COM-07, PROG-01 | Systems |  | Not Started | Normal victory applies each reward exactly once and displays the actual result.
BOSS-01 | M5 Integration and QA | Boss | Configure Stage 1-5 boss statistics and boss-specific completion behavior. | P0 | S | COM-07, DATA-02 | Combat Systems |  | Not Started | The boss uses 80 HP, AC 7, +2 attack, 2D4 damage, and opens RunComplete on victory.
UI-01 | M5 Integration and QA | Menu UI | Build the main menu and Start Game action. | P0 | S | SET-03, FLOW-03 | UI |  | Not Started | Start Game initializes a clean run and opens Stage 1-1.
UI-02 | M5 Integration and QA | Result UI | Build normal result, defeat, and retry panels. | P0 | M | COM-07, COM-08 | UI |  | Not Started | Each panel shows the correct information and exposes only valid actions.
UI-03 | M5 Integration and QA | Completion UI | Build the run-complete screen and return-to-menu action. | P0 | S | BOSS-01, FLOW-03 | UI |  | Not Started | Boss victory opens the screen and returning to the menu clears the run.
QA-01 | M5 Integration and QA | EditMode Tests | Add tests for hex generation, neighbors, distance, movement range, and pathfinding. | P1 | M | HEX-05 | QA |  | Not Started | The grid test suite covers the 37-cell board and representative edge cases.
QA-02 | M5 Integration and QA | EditMode Tests | Add tests for stage rules, dice rules, rewards, leveling, events, and retry snapshots. | P1 | L | FLOW-01, COM-08, NODE-04, PROG-03 | QA |  | Not Started | Tests cover every approved rule and fail when a boundary condition is intentionally broken.
QA-03 | M5 Integration and QA | PlayMode Tests | Add smoke tests for new run, combat return, boss completion, and run reset. | P1 | L | UI-03, QA-02 | QA |  | Not Started | The critical scene flow completes without exceptions in PlayMode tests.
QA-04 | M5 Integration and QA | Acceptance Test | Run the complete MVP acceptance checklist and record defects. | P0 | L | QA-01, QA-03 | Whole Team |  | Not Started | All specification acceptance criteria pass or have documented blocking defects.
DOC-01 | M5 Integration and QA | Documentation | Update team documents and diagrams after implementation decisions change. | P1 | S | QA-04 | Tech Lead |  | Not Started | The specification, architecture, diagrams, and backlog match the delivered build.